## Sprint Backlog
Outputs From Sprint 2 Planning meeting
1.Sprint Backlog
3 developers->120H
# | Epic | User Story | Tasks | Priority | Ready to be planned | Assignee | Estimate | Planned Dielivery Sprint | Task Status
As a < type of user >, I want < some goal > so that < some reason >
1 | Create Account | As a user I want to create account so that I can login to system | 1.Create DB Table | High | yes | Fatma | 1H | 2 | Ongoing
|  |  | 2.Create Signup and login Pages |  |  |  | 5H |  | Not Started
|  |  | 3.Develop backend |  |  |  | 4H |  | Not Started
|  |  | 4.Login with gmail and facebook implementation |  |  |  | 5H |  | Not Started
2 | View Restaurants | As a user I want to view restaurants so that I can select restaurant to order from | 1.Create DB Tables | High | yes | Mostafa | 1H | 2 | Not Started
|  |  | 2.Create Home and resturent page |  |  |  | 20H |  | Not Started
|  |  | 3.Connect with google maps to check nearby resturements |  |  |  | 14H |  | Not Started
|  |  | 4.Filters and sorting for resturents list |  |  |  | 5H |  | Not Started
3 | Search Restaurants | As a user I want to search restaurants so that I can find resturenet I want | 1.Add Search icon in all app pages | Moderate | yes | Omar | 4H | 2 | Not Started
|  |  | 2.develop search in backend |  |  |  | 6H |  | Not Started
4 | View Menu | As a user I want to view menu of any restaurants so that I see menu items and prices | 1.Menu Page basic UI | High | yes | Fatma | 10H | 2 | Not Started
|  |  | 2.Backend |  |  |  | 10H |  | Not Started
|  |  | 3.Show resturnet info and reviews |  |  |  | 5H |  | Not Started
5 | Add to Cart | As a user I want to add to cart so that I can add this item to total order | 1.Create Cart UI | High | yes | Omar | 10H | 2 | Not Started
|  |  | 2.Create DB table |  |  |  | 1H |  | Not Started
|  |  | 3.Develop backend |  |  |  | 19H |  | Not Started
2.Sprint Goal
The main goal for Sprint 2 is to finish demo for add to cart with search functionality